## December 2016
MINES AND GEOSCIENCES BUREAU - REGIONAL OFFICE NO. 6
ACCOMPLISHMENT REPORT
For the Month of December CY 2016
CODE - PROGRAM/ACTIVITY/PROJECT | [5 empty] | MFO CODE | PERFORMANCE INDICATOR (UWM) |  | TOTAL | [15 empty] | TARGET | TARGET |  | ACCOMPLISHMENT |  |  |  | Remarks
[9 empty] | Jan | Feb | March | Q1 | Apr | May | Jun | Q2 | Jul | Aug | Sept | Q3 | Oct | Nov | Dec | Q4 | Annual | This Month | To Date | This Month | To Date | % Accom as of this month | % Accom as to Date
A.01 | GENERAL ADMINISTRATION AND SUPPORT SERVICES
| A.01.a | General Management and Supervision
|  | A.01.a.1 | Administrative Services
|  |  | a. | Management and Administrative |  |  | Reports submitted (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
Support Service
|  |  | b. | Housekeping, Building and Ground |  |  | Reports submitted (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
Improvement Service
|  |  | c. | Human Resource Management Service |  |  | Reports submitted (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
|  |  | d. | Solid Waste Management Service |  |  | Reports submitted (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
|  |  | e. | Implementation of Gov't. Procurement |  |  | Reports submitted (no.) |  | 1 |  |  | 1 | [12 empty] | 1 |  | 1 |  | 1 |  | 100%
|  |  | f. | Cashiering |  |  | Report of checks issued (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
[7 empty] | Paid payrolls and checks prepared (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
Advice of checks issued and cancelled
[8 empty] | (ACIC) (no.) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
Report of remittance of collections and
[8 empty] | deposits to Treasury (no.) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
[7 empty] | Report on revenue collection (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
| A.01.a.2 |  | Financial Management Services
|  |  | a. | Budget Proposals
|  |  |  | a.1 | Forward Estimates |  | FE report submitted (no.) | [5 empty] | 1 |  |  | 1 | [8 empty] | 1 |  | 1 |  | 1 |  | 100%
|  |  |  | a.2 | Budget Proposal and Report Forms |  | Proposed budget submitted (no.)
[8 empty] | a. DMB |  | 12 | 22 | 34 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 34 |  | 34 |  | 34 |  | 100%
[8 empty] | b. Senate/Congress |  |  |  | 0 |  |  | 48 | 48 |  |  |  | 0 |  |  |  | 0 | 48 |  | 48 |  | 48 |  | 100%
|  |  | b. | Budget Execution
|  |  |  | b.1 | Cash Program |  | Cash program and ABM submitted (no.) | [13 empty] | 1 |  |  | 1 | 1 |  | 1 |  | 1 |  | 100%
|  |  |  | b.2 | Monthly Estimate of Income |  | Monthly Estimate of Income submitted (no.) |  | 1 |  |  | 1 | [12 empty] | 1 |  | 1 |  | 1 |  | 100%
|  |  | c. | Account Monitoring and Control
|  |  |  | c.1 | Budget Reports |  | For MGB/DENR/DBM/COA submissions:
[7 empty] | Weekly Financial Performance Report |  | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 48 | 4 | 48 | 4 | 48 | 100% | 100%
[7 empty] | Monthly Budget Reports (no.) |  | 5 | 5 | 5 | 15 | 5 | 5 | 5 | 15 | 5 | 5 | 5 | 15 | 5 | 5 | 5 | 15 | 60 | 5 | 60 | 5 | 60 | 100% | 100%
[7 empty] | Quarterly Budget Reports (no.) |  | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 12 |  | 12 |  | 12 |  | 100%
[7 empty] | Annual Budget Reports (no.) | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100%
|  |  |  | c.2 | Accounting Reports |  | Financial Accounting Reports:
[7 empty] | Weekly Financial Performance Report |  | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 48 | 4 | 48 | 4 | 48 | 100% | 100%
[7 empty] | Monthly Financial Reports (no.) |  | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 24 | 2 | 24 | 2 | 24 | 100% | 100%
[7 empty] | Quarterly Financial Accountability Reports (no.) |  | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 12 |  | 12 |  | 12 |  | 100%
[7 empty] | Annual Financial Accountability Reports (no.) | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100%
Financial Statements:
[7 empty] | Monthly Financial Reports (no.) |  | 11 | 11 | 11 | 33 | 11 | 11 | 11 | 33 | 11 | 11 | 11 | 33 | 11 | 11 | 11 | 33 | 132 | 11 | 132 | 11 | 132 | 100% | 100%
[7 empty] | Quarterly Schedules Budget Reports (no.) | [5 empty] | 9 |  |  | 9 | 9 |  |  | 9 | 9 |  |  | 9 | 27 |  | 27 |  | 27 |  | 100%
[7 empty] | Quarterly Financial Statements (no.) | [5 empty] | 4 |  |  | 4 | 4 |  |  | 4 | 4 |  |  | 4 | 12 |  | 12 |  | 12 |  | 100%
[7 empty] | Annual Schedules |  |  | 15 |  | 15 | [12 empty] | 15 |  | 15 |  | 15 |  | 100%
[7 empty] | Annual Financial Statements (no.) |  |  | 8 |  | 8 | [12 empty] | 8 |  | 8 |  | 8 |  | 100%
| A.01.a.3 |  | Planning and Policy Formulation
|  |  | a. | Preparation/Endorsement of Plans |  |  | Work and financial plan finalized (no.) |  |  |  | 1 | 1 | [12 empty] | 1 |  | 1 |  | 1 |  | 100%
|  |  |  | and Programs |  |  | Proposed budget submitted (no.) |  |  |  | 1 | 1 | [12 empty] | 1 |  | 1 |  | 1 |  | 100%
|  |  | b. | Program Monitoring and Evaluation |  |  | Consolidated physical accomplishment
[8 empty] | reports submitted (no.) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
[7 empty] | Validation reports submitted (no.) | [14 empty] | 1 |  | 1 | 1 |  | 1 |  | 1 |  | 100%
[7 empty] | Semi-Annual/Annual report prepared |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 2 |  | 2 |  | 2 |  | 100%
|  |  | c. | Policy Development Formulation |  |  | Policies reviewed (no.) |  |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 |  | 1 | 1 | 2 | 8 | 1 | 8 | 1 | 8 | 100% | 100%
|  |  |  | of Mineral Policies |  |  | National Conferences attended/
[8 empty] | participated (no.) |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 | 4 | 1 | 4 |  | 4 |  | 100%
| A.01.a.4 |  | Conduct of Investigation and Provision of |  |  |  | Legal assistance provided (no.)
|  |  | Legal Assistance |  |  |  | Hearings attended (no.)
| A.01.b | Human Resource Development
|  | b.1 | Human Resource Development Service
|  |  | a. | Management of Training and Career |  |  | Reports prepared (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 12 | 100% | 100%
Development Programs
A.02 | SUPPORT TO OPERATION
A.03 | OPERATIONS
MFO 1: MINERAL RESOURCE DEVELOPMENT SERVICES
[5 empty] | Quantity: |  | number of new mineral reservation areas
assessed/endorsed for declaration
[5 empty] | Quality: |  | percentage of area surveyed that is
identified as mineral reservation
[5 empty] | Quality: |  | percentage of stakeholders who rate the
quality of MGB mineral reservation maps
as good or better
[5 empty] | Quality: |  | percentage increase in Peso value for
royalty payments collected
| A.03.a | Mineral Resource Services |  |  |  | 1
| A.03.a.1 |  | Communication Plan for
Minerals Development
|  |  | A.03.a.1.a | Conduct Awareness and |  |  | 1. | Stakeholder's forum (no.)
|  |  |  | Advocacy on Mineral Resources |  |  |  | a. Dialogues with Sangguniang
|  |  |  | and Geosciences (MRGS) |  |  |  | Panlalawigan | [9 empty] | 2 | 2 | 4 | 2 |  |  | 2 | 6 |  | 6 |  | 6 |  | 100%
b. Dialogues with other groups
[8 empty] | (Religious, CSO, Academe, etc.) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 |  | 13 |  | 108.3%
[7 empty] | 2. | IEC Activities (Multi-media Campaign)
[8 empty] | a. Radio/TV guestings (no.) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 2 | 16 | 200% | 133.3% | see attachment
b. Press releases/photo releases/
[8 empty] | feature stories (no.) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 1 | 16 | 100% | 133.3% | see attachment
|  |  | A.03.a.1.b | Capacity Building on MRGS |  |  | Workshops/training conducted/
|  |  |  | laws, rules and regulations |  |  |  | coordinated/participated on: (no.)
[7 empty] | 1. | MGB personnel | [6 empty] | 2 | 2 |  |  | 1 | 1 |  | 4 |  | 4 | 7 |  | 7 |  | 7 |  | 100%
[7 empty] | 2. | LGUs and other stakeholders |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  |  |  | 3 |  | 3 |  | 3 |  | 100%
[7 empty] | 3. | Small Scale Miners | [6 empty] | 1 | 1 |  |  | 1 | 1 |  |  |  |  | 2 |  | 2 |  | 2 |  | 100%
|  |  | A.03.a.1.c | Generate/Publish/ Disseminate |  |  | 1. | Website maintained (no.) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100%
|  |  |  | Information and IEC Materials |  |  |  | 1.1 Articles posted | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 24 | 2 | 24 | 3 | 27 | 150% | 112.5% | see attachment
[7 empty] | 2. | IEC materials produced |  | 1 |  | 1 |  |  | 1 | 1 | [8 empty] | 2 |  | 2 |  | 2 |  | 100%
[7 empty] | 3. | IEC materials reproduced/distributed (no.) | [6 empty] | 50 | 50 | [5 empty] | 50 |  | 50 | 100 |  | 100 |  | 115 |  | 115%
[7 empty] | 4. | Statistics reports submitted to MGBCO (no.) | 11 |  |  | 11 | 7 |  |  | 7 | 7 |  |  | 7 | 7 |  |  | 7 | 32 |  | 32 |  | 32 |  | 100%
[7 empty] | 5. | Maps/Map Info Database submitted to
[8 empty] | MGBCO (no.) | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 24 | 2 | 24 | 2 | 24 | 100% | 100%
[7 empty] | 6. | MRGS reports submitted to MGBCO (no.) | 7 | 2 | 2 | 11 | 5 | 2 | 2 | 9 | 6 | 2 | 2 | 10 | 5 | 2 | 2 | 9 | 39 | 2 | 39 | 2 | 39 | 100% | 100%
|  |  | A.03.a.1.d | National Linkages |  |  | Linkages coordinated (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 |  | 14 |  | 116.7%
| A.03.a.2 |  | National Mineral Reservation Program
|  |  | 1. | Management of Existing Mineral |  |  | Mineral Reservations Area rights managed/
|  |  |  | Reservations |  |  |  | monitored (no.)
|  |  | 2. | Establishment of New Mineral |  |  | Areas assessed/endorsed for declaration (no.) | [14 empty] | 1 |  | 1 | 1 |  | 1 |  | 1 |  | 100%
Reservation Areas
|  |  | 3. | Research and Development/ |  |  | Research/Studies conducted/developed (no.)
Special Projects
|  |  | 4. | Mineral Reservation Program |  |  | MGB Facilities/Equipment upgraded/
|  |  |  | Administration |  |  |  | maintained/enhanced (no.)
| A.03.b | Geosciences Development Services
| A.03.b.1 |  | Geohazard Survey and Assessment
|  |  | A.03.b.1.a | Identification and Mapping of
Critical Land Areas
|  |  | 1. | Field Mapping and Survey
|  |  |  | a. | Vulnerability and Risk Assessment |  | LGUs assessed
[5 empty] | (VRA) |  |  | a. Municipalities/Cities (no.) |  |  | 2 | 2 | 2 |  | 2 | 4 | 2 | 2 | 2 | 6 |  |  |  |  | 12 |  | 12 |  | 12 |  | 100%
[8 empty] | b. Geohazard Report prepared (no.) | [6 empty] | 2 | 2 | 2 |  | 2 | 4 | 2 | 2 | 2 | 6 | 12 | 2 | 12 |  | 12 |  | 100%
|  |  |  | b. | Updating of 1:10,000 scale |  | LGUs assessed
[5 empty] | geohazard maps as a result of |  |  | a. Municipalities/Cities (no.) |  |  | 1 | 1 | [12 empty] | 1 |  | 1 |  | 1 |  | 100%
[5 empty] | changes due to natural calamities |  |  | b. Geohazard Report prepared (no.) |  |  |  |  | 1 |  |  | 1 | [8 empty] | 1 |  | 1 |  | 1 |  | 100%
|  |  |  | c. | Detailed Sub-surface assessment |  | LGUs assessed
[8 empty] | a. Municipalities/Cities (no.) | [10 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 100%
[8 empty] | b. Geohazard Report prepared (no.) | [13 empty] | 1 |  | 1 | 1 |  | 1 |  | 1 |  | 100%
|  |  | 2. | Production of Geohazard/VRA Maps |  |  | Geohazard/VRA Maps prepared (no.) | [5 empty] | 1 | 3 | 4 | 8 |  | 4 | 4 | 8 | 4 | 5 |  | 9 | 25 |  | 25 |  | 25 |  | 100%
|  |  | 3. | Geohazard IEC Materials Dissemination |  |  | a. | Maps disseminated (no.) | [13 empty] | 133 |  | 133 | 133 |  | 133 |  | 133 |  | 100%
[7 empty] | b. | Posters disseminated |  | 50 | 150 | 200 | 100 |  | 200 | 300 | 100 | 100 | 100 | 300 | 150 | 50 |  | 200 | 1000 |  | 1000 |  | 1088 |  | 108.8%
[7 empty] | c. | VCDs disseminated (no.) |  | 5 | 5 | 10 | 5 |  | 15 | 20 | 5 | 5 | 5 | 15 | 10 | 5 |  | 15 | 60 |  | 60 |  | 60 |  | 100%
[7 empty] | d. | Pamphlets/flyers disseminated (no.) |  | 50 | 50 | 100 | 50 |  | 50 | 100 | 50 | 50 | 50 | 150 | 100 | 50 |  | 150 | 500 |  | 500 |  | 642 |  | 128.4%
[7 empty] | e. | Signages provided/installed | [8 empty] | 1 |  | 1 | 2 |  |  |  |  | 2 |  | 2 |  | 3 |  | 150%
[7 empty] | f. | Quadrangle geohazard maps uploaded
[8 empty] | in website (no.) | [16 empty] | 0
[7 empty] | g. | Tri-media (no.) | [6 empty] | 1 | 1 | 1 |  | 1 | 2 | 1 |  |  | 1 | 4 |  | 4 |  | 5 |  | 125%
|  |  | 4. | Capacity Building |  |  | Trainings/seminars for MGB technical
[8 empty] | personnel (no.) |  |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 3 | 5 | 1 | 5 | 1 | 9 | 100% | 180%
|  |  | 5. | Conduct of IEC to LGUs |  |  | a. | Consultation/Seminars/Workshops for
|  |  |  | (IEC campaign on Geohazard and VRA) |  |  |  | Brgy. Captains & officials conducted (no.) |  | 100 | 100 | 200 |  |  | 50 | 50 | 200 | 200 | 250 | 650 | 200 | 200 |  | 400 | 1300 |  | 1300 | 9 | 1309 |  | 100.7% | see attachment (unreported in November)
[7 empty] | b. | Lectures presented (no.) | [6 empty] | 2 | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 6 |  | 6 |  | 6 |  | 100%
[7 empty] | c. | Advisories issued (no.) |  |  | 5 | 5 | [8 empty] | 5 |  |  | 5 | 10 |  | 10 |  | 10 |  | 100%
[7 empty] | d. | Activity/exit reports issued (no.) |  |  | 3 | 3 | 2 |  | 2 | 4 | 2 | 2 | 3 | 7 |  |  |  | 0 | 14 |  | 14 |  | 14 |  | 100%
|  |  | 6. | Geohazards Operation Center |  |  | Geohazards Operation Center maintained (no.) |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100%
[8 empty] | Advisories re-issued (no.) | [12 empty] | 66 |  |  | 66 | 66 |  | 66 |  | 133 |  | 201.5%
[8 empty] | Incident/flash reports prepared (no.) | [12 empty] | 1 |  |  | 1 | 1 |  | 1 |  | 3 |  | 300%
[8 empty] | PDRA meetings attended (no.) | [12 empty] | 1 |  |  | 1 | 1 |  | 1 |  | 6 |  | 600%
|  |  | A.03.b.1.b | Coastal Geohazard and Impact
of Climate Change
|  |  | 1. | Field Mapping and Survey
|  |  |  | 1:10,000 Scale |  |  | LGUs assessed
[8 empty] | a. Municipality (no.) |  |  | 2 | 2 | 1 |  |  | 1 | 4 |  |  | 4 | 2 |  |  | 2 | 9 |  | 9 |  | 9 |  | 100%
[8 empty] | b. Reports with maps prepared (no.) | [5 empty] | 2 | 1 | 3 |  |  | 4 | 4 |  | 2 |  | 2 | 9 |  | 9 |  | 9 |  | 100%
|  |  | 2. | Production of Coastal Geohazard Maps |  |  | Coastal Geohazard/VRA Maps prepared (no.) | [17 empty] | 0
[7 empty] | Advisories issued (no.) |  |  |  | 6 | 6 | 3 |  | 12 | 15 |  |  |  |  | 6 |  |  | 6 | 27 |  | 27 |  | 27 |  | 100%
[7 empty] | Activity/exit report (no.) | [5 empty] | 2 | 1 |  | 3 |  | 4 |  | 4 |  | 2 |  | 2 | 9 |  | 9 |  | 9 |  | 100%
|  |  | 3. | Operation and Maintenance of RPS
Explorer (Central Office only)
|  |  | 4. | Capacity Building |  |  | Trainings/seminars for MGB technical
personnel (no.)
|  |  | 5. | Conduct of IEC to LGUs |  |  | a. | Municipal LGUs (no.)
[7 empty] | b. | Seminars/workshops/lectures
conducted (no.)
| A.03.b.2 |  | Geological Mapping
|  |  | A.03.b.2.a | Quadrangle Geological Mapping and |  |  | Areas surveyed | [5 empty] | 1 |  |  | 1 |  |  | 1 | 1 |  |  |  |  | 2 |  | 2 |  | 2 |  | 100%
|  |  |  | Surveys (Land & Coastal Zones) |  |  | Geologic Reports with Map prepared (no.) | [7 empty] | 1 | 1 | [5 empty] | 1 |  | 1 | 2 |  | 2 |  | 2 |  | 100%
|  |  | A.03.b.2.b | Mineral Exploration (Central Office)
|  |  | A.03.b.2.c | Laboratory Services |  |  | Samples analyzed (no.)
Determinations made (no.)
|  |  | A.03.b.2.d | Mineral Resources Inventory |  |  | Provincial resource maps updated
[8 empty] | and submitted to MGB-CO | [13 empty] | 1 |  | 1 | 1 |  | 1 |  | 1 |  | 100%
| A.03.b.3 |  | Groundwater Resources Assessment
|  |  | a. | Groundwater Resource Assessment |  |  | LGUs assessed
a. Municipality (no.)
[8 empty] | b. Province (no.) | [8 empty] | 1 |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 100%
Hydrogeologic reports with 1:250,000
[8 empty] | groundwater availability map (no.) | [10 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 100%
| A.03.b.4 |  | Miscellaneous Geological Services
|  |  | a. | Technical Assistance Provided |  |  | a. | Investigation reports prepared (no.) | [5 empty] | 5 |  | 5 | [5 empty] | 5 |  | 5 | 10 |  | 10 |  | 14 |  | 140%
|  |  |  | (GIR/GVR/EGGAR/SLF) |  |  | b. | Clients served (no.) |  | 2 | 2 | 4 | 2 | 2 | 2 | 6 | 1 | 1 | 1 | 3 | 1 | 1 |  | 2 | 15 |  | 15 |  | 105 |  | 700%
MFO 2. | MINING REGULATION SERVICES
| A.03.c | Mineral Lands Administration
PI 1 Permit Issuance
[5 empty] | Quantity: |  | number of mining permits/contracts issued
and agreements endorsed for approval
[5 empty] | Timeliness: |  | percentage of agreements entered into
within 4 months from tendering
| A.03.c.1 |  | Mineral Investment Promotion Program
|  |  | A.03.c.1.a | Issuance of mining contracts/permits
including areas within mineral
reservations and other related permits
|  |  |  | A.03.c.1.a.1 | Issuance of Permits/Contracts |  | Mining rights/contracts/permits endorsed to
Central Office/DENR for clearance (no.)
a. Agreements/contracts/permits (no.)
[8 empty] | (FTAA, MPSA, EP, ISAGP, MPP) | [6 empty] | 1 | 1 |  | 1 |  | 1 |  |  |  |  | 2 |  | 2 |  | 3 |  | 150%
b. Ore Transport Permit (OTP)/
Certification (no.)
[8 empty] | - OTP | [20 empty] | 1
[8 empty] | - Certifications | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 12 | 1 | 12 | 2 | 19 | 200% | 158.3%
c. Others
[8 empty] | - Accreditations | 2 | 2 | 3 | 7 | 2 | 2 | 3 | 7 | 2 | 3 | 3 | 8 | 2 | 3 | 3 | 8 | 30 | 3 | 30 | 4 | 66 | 133.3% | 220%
[8 empty] | -CEMCRR/CoE | [6 empty] | 1 | 1 | [5 empty] | 2 |  | 2 | 3 |  | 3 |  | 9 |  | 300%
d. Mineral Ore Export Permit (MOEP)
-issued
|  |  |  | A.03.c.1.a.2 | Use It or Lose It Policy |  | a. | Mining applications with final action (no.) |  |  |  |  | 1 |  |  | 1 | 1 | 2 |  | 3 |  |  |  |  | 4 |  | 4 |  | 4 |  | 100%
[7 empty] | b. | Mining permits/contracts reviewed/
[8 empty] | endorsed for cancellation (no.) | 3 | 3 | 3 | 9 | 3 | 3 | 3 | 9 | 3 | 3 | 3 | 9 | 3 | 4 |  | 7 | 34 |  | 34 |  | 34 |  | 100% | The actual accomplishment is 34.
|  |  |  | A.03.c.1.a.3 | Approval of SHES Programs |  | 1. | EPEP/FMRDP/PEIR endorsed to MRFC (no.) |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 3 |  | 3 |  | 3 |  | 100%
[7 empty] | 2. | Annual EPEP approved (no.) | 7 | 8 |  | 15 | [12 empty] | 15 |  | 15 |  | 19 |  | 126.7%
[7 empty] | 3. | SDMP/CDP approved (no.) | [5 empty] | 1 |  | 1 | 1 |  | 1 | 2 |  | 2 |  | 2 | 5 |  | 5 | 3 | 5 |  | 100% | see attachment
[7 empty] | 4. | Annual SDMP approved (no.) |  | 7 | 8 | 15 | [12 empty] | 15 |  | 15 | 3 | 19 |  | 126.7% | see attachment
[7 empty] | 5. | Annual Safety and Health Programs
[8 empty] | approved/CMP (no.) | 10 | 10 | 10 | 30 | [12 empty] | 30 |  | 30 |  | 33 |  | 110%
[7 empty] | 6. | Environmental Work Program endorsed
[8 empty] | to MMD (no.) | [12 empty] | 1 |  |  | 1 | 1 |  | 1 |  | 6 |  | 600%
[7 empty] | 7. | NGP Monitoring Reports submitted (no.) | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 4 |  | 4 |  | 4 |  | 100%
|  |  | A.03.c.1.b | Assistance to P/CMRB LGUs/ |  |  | 1. | Provinces Inventoried for Small Scale
|  |  |  | other stakeholders |  |  |  | Mining Sites (no.) |  | 1 |  | 1 | 1 | 1 |  | 2 |  | 1 | 1 | 2 | 1 |  |  | 1 | 6 |  | 6 |  | 6 |  | 100%
[7 empty] | 2. | Minahang Bayan Sites identified (no.) | [9 empty] | 1 |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 100%
[7 empty] | 3. | Minahan Bayan Sites endorsed to DENR
[8 empty] | through MGBCO (no.) | [13 empty] | 1 |  | 1 | 1 |  | 1 | 1 | 1 |  | 100% | Nabas, Aklan
[7 empty] | 4. | P/CMRBs operationalized (no.) | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 100% | 100%
[7 empty] | 5. | P/CMRBs reconstituted (no.)
[7 empty] | 6. | Meetings conducted/participated (no.) | 3 | 3 | 4 | 10 | 3 | 3 | 4 | 10 | 3 | 3 | 4 | 10 | 5 | 5 |  | 10 | 40 |  | 40 | 2 | 54 |  | 135%
[7 empty] | 7. | P/CMRB regional consultations
[8 empty] | conducted (no.) | [10 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 100%
PI 2 Monitoring
[5 empty] | Quantity: |  | number of sites and facilities monitored and/or
inspected with reports issued
[5 empty] | Quality: |  | percentage of agreements with one or more
violations over the last 3 years
[5 empty] | Timliness: |  | percentage of sites that have been inspected
more than twice in the last 2 years
| A.03.c.2 |  | Mining Industry Development Program
|  |  | A.03.c.2.a | Monitor/audit of approved mining |  |  | 1. | Permit areas/projects monitored (no.)
|  |  |  | contracts/permits including areas |  |  |  | 1.1 Work Program | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 4 | 4 | 4 | 12 | 4 | 5 |  | 9 | 45 |  | 45 |  | 47 |  | 104.4%
|  |  |  | within mineral reservations as to |  |  |  | 1.2 Safety, Health, Environment and
|  |  |  | compliance to the implementation |  |  |  | Socials Programs
|  |  |  | of approved Work Program and |  |  |  | a. No. of permits/contracts | 6 | 4 | 4 | 14 | 5 | 6 | 5 | 16 | 3 | 1 |  | 4 |  |  |  |  | 34 |  | 34 |  | 45 |  | 132.4%
|  |  |  | Safety, Health, Environment and |  |  |  | b. No. of monitoring | 6 | 4 | 4 | 14 | 5 | 6 | 5 | 16 | 5 | 5 | 5 | 15 | 6 | 5 |  | 11 | 56 |  | 56 |  | 64 |  | 114.3%
Socials Program
1.3 Monitoring report on Mining Forest
[8 empty] | Program (no.) | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 2 |  | 2 |  | 2 |  | 100%
|  |  | A.03.c.2.b | Strengthen Multi-Partite |  |  | 1. | Multi-partite Monitoring Teams (MMT)
|  |  |  | Monitoring System |  |  |  | operationalized (no.) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 100% | 100%
|  | A.03.c.3 | Mine Rehabilitation Program
Abandones/Inactive Mines
|  |  | a. | Bagacay Mine area |  |  | Rehabilitation plan/measures
implemented (no.)
|  |  | b. | Other Abandones Mine Sites
|  |  |  | 1. | Reconnaisance Survey
|  |  | A.03.c.3.b | Risk Assessment of other inactive |  |  | Rehabilitation plan/mitigating plan
|  |  |  | mining areas/sites conducted (no.) |  |  |  | prepared/implemented (no.)
|  |  | A.03.c.3.c | Marcopper |  |  | Monitoring reports submitted to MGBCO (no.)
PI 3 Enforcement
[5 empty] | Quantity: |  | number of violations or complaints acted upon
with reports issued
[5 empty] | Quality: |  | percentage of submitted reports that
resulted in the issuance of notice of
violations and penalties imposed
[5 empty] | Timeliness: |  | percentage of complaints or defected
violations that are acted upon earlier
than the prescribed period
|  | A.03.c.4 | Resolution of Complaints/Cases/Conflicts |  |  |  | Number of complaints/cases/conflicts
investigated/resolved (no.)
[8 empty] | 1. MGB |  |  | 1 | 1 |  | 1 | 1 | 2 |  | 1 | 1 | 2 | 1 | 2 |  | 3 | 8 |  | 8 | 4 | 11 |  | 137.5%
[8 empty] | 2. Panel | [10 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 100%
2.b Quarterly Accomplishment/Inventory
[8 empty] | Report of the Panel of Arbitrators (no.) |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 | 4 | 1 | 4 | 1 | 4 | 100% | 100%
3. Complaints filed with the Provincial/
[8 empty] | City Prosecutor's Office | [12 empty] | 1 |  |  | 1 | 1 |  | 1 | 1 | 1 |  | 100%
|  | A.03.c.5 | Anti-Illegal Mining |  |  |  | Illegal Mining Sites with Cease and Desist
Order (CDO)/Seizure/Confiscation order
[8 empty] | issued/implemented (no.) | [6 empty] | 1 | 1 | [8 empty] | 1 |  | 1 |  | 1 |  | 100%
Prepared by: | [24 empty] | Noted:
CECILIA L. OCHAVO-SAYCON | [24 empty] | LEO VAN V. JUGUAN, CESO V
Chief, FAD/Planning Officer | [24 empty] | Regional Director

## Attachment
Mines and Geosciences Bureau Region 6
ATTACHMENT / December CY 2016
IEC Activities (Radio/TV Guestings)
1 | Interview of RD Juguan by Bombo Radyo and RMN Re: Assessment of MGB on the volume of available SAG materials in the Province of Iloilo Nov. 9, 2016 Iloilo Provincial Capitol
2 | ABS-CBN - Interview of RD Juguan (over the phone) Re: STL Dredging Nov. 29, 2016
PRESS RELEASES and ARTICLES POSTED ON WEBSITE
Website Maintained - www.mgb6.org
Title
1 | FIVE POLICY DIRECTIONS FOR THE COUNTRY'S MINERALS INDUSTRY (An Excerpt from the Keynote Speech 63rd Annual National Mine Safety Environment Conference Philippine Mine Safety and Environment Association) | Posted on the website, released to the PIA and local media
2 | Gender and Development Re-Orientation of MGB RO6 Held | Posted on the website
3 | Training of Dr. Leilanie Suerte in Japan | Posted on the website
SDMP Approved / Annual SDMP Approved
1. Kimwa-Iloilo Construction and Development Corp. (Pavia Project)
2. Jacareed Enterprises
3. Kimwa-Iloilo Construction and Development Corp. (San Miguel Project)
LIST OF BARANGAYS PROVIDED WITH IEC ON 1:10,000 SCALE GEOHAZARD MAPS (unreported in November)
Province | Municipality | Barangay
Iloilo | Cabatuan | 1 | Ayaman
|  | 2 | Balabag
|  | 3 | Cagban
|  | 4 | Gaub
|  | 5 | Ingas
|  | 6 | Janipaan Olo
|  | 7 | Pacatin
|  | 8 | Tiring
|  | 9 | Tuy-an

## PIR (hidden)
PROGRAM INFORMATION REPORTING
|  |  |  | Month: | March |  | 2016
MFO I : MINERAL RESOURCES DEVELOPMENT SERVICE
PI 1: | Number of New Mineral Reservation Area Assessed/Endorsed for Declaration (location)
PI 2: | Percentage of Area Surveyed that is Identified as a Mineral Reservation
Location |  |  | Area (Hectares) |  |  | Date of Survey (Geological/ Geographical) |  |  | Area Surveyed (Hectares) |  | %
PI 4: | Percentage of Increase in Peso Value for Royalty Payments Collected
Projected Amount of Royalty to be Collected for 2015 (PhP) |  |  |  | Actual Amount of Royalty Collected for 2015 (PhP) |  |  |  | Percentage Increase (%)
PI 5 : | Percentage of Philippine Territory Surveyed (Geological Exploration) at least once in the Last 3 Years
Location of Area Surveyed |  |  |  | Area Surveyed (Hectares) |  |  |  | Date of Survey |  |  | %
MFO 2 : MINING REGULATION SERVICES
Permit Issuance
PI 1: | Number of Mining Permits/Contracts Issued and Agreements Endorsed for Approval
PI 2: | Percentage of Agreements Entered into within 4 Months from Tendering
Type of Permit/ Contract |  |  | Applicant |  |  | Date Filed |  | Date Issued/ Indorsed |  | Endorsed/Issued w/in 4 Months (Yes/No)
CEMCRR 277-15 R-VI |  |  | Republic Aggregates and Concrete Enterprises Corp |  |  | 2015-12-09 |  | 2015-12-16 |  | Yes
No. of Mining Permits/Contracts issued and Agreements Endorsed for Approval: 1 | [6 empty] | Permits/Contracts/Agreements issued within 4 months: 1
% of Permits/Contracts/ Agreements issued w/in 4 mos. : 100%
Monitoring
PI 1: | Number of Sites and Facilities Monitored and/or Inspected with Reports Issued
PI 2: | Percentage of Agreements with 1 or More Violations over the Last 3 Years
PI 3: | Percentage of sites that have been inspected more than twice in the last 2 years
Sites/Facilities (Permits/Contracts) Inspected/Monitored |  |  |  | 2016 |  | 2015 |  |  |  | 2014
|  |  |  | Date of Inspection | Number of Violations | Date of Inspection | Number of Violations |  | Date of Inspection | Number of Violations
WORK PROGRAM
MPSA
IC Bertumen Co., Inc. (MPSA 231-007VI) | [5 empty] | 2015-03-10 |  |  | 2014-06-19 | 1 (conducting exploration with expired exploration period)
Minimax Min. Expl'n. Corp. (MPSA 135-99VI) | [5 empty] | 2015-03-11 |  |  | 2014-06-17
Silicon Dev't. Corp. (MPSA 204-2004VI) |  |  |  | 02/3-13/2016 |  | 3/3-4/2015 |  |  | 11/3-4/2014 | 1 (non-renewal of exploration period for more than 5 years)
Maricalum Mining Corp. (MPSA 120-98-VI) | [5 empty] | 5/1-2/2015 | 1 (non payment of occupation fee) |  | 2014-01-27 | 1 (non payment of occupation fee)
Philex Gold Phil., Inc. (MPSA 096-97-VI) | [5 empty] | 5/1-2/2015 |  |  | 2014-01-29
Selenga Mining Corp. (MPSA 217-2005VI) | [5 empty] | 5/1-2/2015 |  |  | 2014-01-30
Quarry Ventures, Phil. Inc. (MPSA 129-98VI) | [5 empty] | 2015-06-11 | 1 (non payment of occupation fee) |  | 2014-09-18 | 1 (non payment of occupation fee)
Teresa Marble Corporation (MPSA 097-97VI) | [5 empty] | 6/9-10/2015 | 1 (non payment of occupation fee) |  | 2014-09-17 | 1 (non payment of occupation fee)
Teresa Marble Corporation (MPSA 107-98VI) | [5 empty] | 2015-06-12 | 1 (non payment of occupation fee) |  | 2014-09-16 | 1 (non payment of occupation fee)
Tudor Min. Expl'n. Corp. (MPSA 270-2001VI) | [5 empty] | 7/15-22/2015 |  |  | 2014-08-27
Far East Cement Corp. (MPSA 326-2010VI) | [5 empty] | 7/15-22/2015 |  |  | 2014-09-28
Vulcan Ind'l. & Mining Corp. (MPSA 092-97VI) | [5 empty] | 9/23-27/2015 |  |  | 2014-11-06
Vulcan Ind'l. & Mining Corp. (MPSA 113-98VI) | [5 empty] | 9/23-27/2015 |  |  | 2014-11-06
San Dominico Min. & Ind'l. Corp. (319-2010-VI) | [5 empty] | 10/19-21/2015 |  |  | 2014-10-04
EP
Vale Expl'n. Phils., Inc. (EP-10-2010VI) | [5 empty] | 3/13-14/2015 |  |  | 2014-06-16
Alcorn/Cosco Capital Inc. (EP-07-2010VI) | [5 empty] | 2015-03-12 |  |  | 2014-06-19
Tambuli Mining Co., Inc. (EP000003VI) |  |  |  | 02/3-13/2016 |  | 3/5-6/2015 |  |  | 2014-10-02
Carles & Cauayan Mining Corp.(EXP000004VI) | [5 empty] | 9/22-27/2015 |  |  | 2014-07-07
PGPI/BMC (EP-08-2010VI) | [5 empty] | 9/22-27/2015 |  |  | 2014-07-09
San Dominico Min. & Ind'l. Corp. (06-2010-VI) | [5 empty] | 10/19-21/2015 |  |  | 2014-10-03
ISAG
153 Landowners Cooperative |  |  |  | 01/21-30/2016 | none | 2/24-25/2015 |  |  | 2014-02-13
Ban Hua U. Flores |  |  |  | 01/21-30/2016 | none | 2/25-26/2015 |  |  | 2014-02-15
Lilen S. Uy |  |  |  | 01/21-30/2016 | none | 2/27-28/2015 |  |  | 2014-02-14
Mountain Aggregates Inc. | [5 empty] | 5/28-29/2015 |  |  | 2014-02-07
John Alexander I. Gayoso |  |  |  | 02/3-13/2016 |  | 2015-06-12 |  |  | 2014-07-02
Stephanie O. Chiu |  |  |  | 02/3-13/2016 |  | 9/9-10/2015 |  |  | 2015-11-07
Jacareed Enterprises |  |  |  | 01/21-30/2016 | none | 9/9-10/2015 |  |  | 2014-02-04
Anecito Mondia |  |  |  | 01/21-30/2016 | none | 9/9-10/2015 |  |  | New
MPP
Mabini Limers & Farmers Multi-Purpose Coop. | [5 empty] | 2015-01-22 |  |  | 2014-10-15
ASPAC Dredging & Restoration |  |  |  | 02/3-13/2016 |  | 1/28-29/2015 |  |  | 2014-11-05
Tanden Realty Dev't. Ventures Corp. | [5 empty] | 1/30-31/2015 |  |  | 2014-11-06
Rocache Aggregate & Dev't. Corp. | [5 empty] | 2015-01-15 |  |  | 2014-02-05
Krushrock Corporation |  |  |  | 01/21-30/2016 | none | 2/23-24/2015 |  |  | 2014-02-12
Mountain Aggregates Inc. | [5 empty] | 5/27-28/2015 |  |  | 2014-02-08
GC&C Aggregates, Inc. |  |  |  | 01/21-30/2016 | none | 2015-05-30 |  |  | 2014-02-06
ALH Lime Factory | [5 empty] | 7/2-3/2015 |  |  | 2014-10-16
Malogo Aggregates Ventures, Inc. |  |  |  | 01/21-30/2016 | none | 9/9-10/2015 |  |  | 2014-07-01
Kimwa Const'n. & Dev't. Corp. | [5 empty] | 9/16-17/2015 |  |  | 2014-10-07
F. Gurrea Const'n. Inc. | [5 empty] | 9/16-17/2015 |  |  | 2014-04-04
ARSD Construction Corporation | [5 empty] | 9/23-24/2015 |  |  | 2014-04-30
Skaff Eximport and Services, Inc. | [5 empty] | 9/23-24/2015 |  |  | 2014-04-28
Seven C Integrated Corporation | [5 empty] | 11/4-7/2015 |  |  | 2014-10-17
AWI Concrete Products & Const. Supply | [5 empty] | 11/4-7/2015 |  |  | 2014-05-05
LGP Builders & Development Corp. | [5 empty] | 11/4-7/2015 |  |  | 2014-10-09
Bernadette Mondejar | [5 empty] | 11/4-7/2015 |  |  | 2014-10-10
Maria Aisa B. Ratcliff |  |  |  | 02/3-13/2016
ISHES
MPSA
IC Bertumen Co., Inc. (MPSA 231-007VI) | [5 empty] | 3/10-16/2015 |  |  | 06/21-22/2014
Minimax Min. Expl'n. Corp. (MPSA 135-99VI) | [5 empty] | 3/10-16/2015 |  |  | 06/19-20/2014
Silicon Dev't. Corp. (MPSA 204-2004VI) |  |  |  | 02/10-11/2016 |  | 3/2-8/2015 |  |  | 02/19-21/2014
Maricalum Mining Corp. (MPSA 120-98-VI) | [5 empty] | 4/27-5/1/2015; 9/23-10/3/2015 |  |  | 7/7-8/2014
Philex Gold Phil., Inc. (MPSA 096-97-VI) | [5 empty] | 4/27-5/1/2015; 9/23-10/3/2015 |  |  | 7/9-10/2014
Selenga Mining Corp. (MPSA 217-2005VI) | [5 empty] | 4/27-5/1/2015; 9/23-10/3/2015 |  |  | 1/31-2/2/2014
Quarry Ventures, Phil. Inc. (MPSA 129-98VI) | [5 empty] | 6/24-7/2/2015 |  |  | 9/19-20/2014
Teresa Marble Corporation (MPSA 097-97VI) | [5 empty] | 6/24-7/2/2015 |  |  | 2014-09-18
Teresa Marble Corporation (MPSA 107-98VI) | [5 empty] | 6/24-7/2/2015 |  |  | 9/16-17/2014
Tudor Min. Expl'n. Corp. (MPSA 270-2001VI) | [5 empty] | 7/15-22/2015 |  |  | 8/20-28/2014
Far East Cement Corp. (MPSA 326-2010VI) | [5 empty] | 7/15-22/2015 |  |  | 8/26-27/204
Vulcan Ind'l. & Mining Corp. (MPSA 092-97VI) | [5 empty] | 9/23-10/3/2015 |  |  | 11/6-7/2014
Vulcan Ind'l. & Mining Corp. (MPSA 113-98VI) | [5 empty] | 9/23-10/3/2015 |  |  | 2014-11-10
San Dominico Min. & Ind'l. Corp. (319-2010-VI) | [5 empty] | 10/19-20 & 26-31/2015 |  |  | 11/3-4/2014
EP
Vale Expl'n. Phils., Inc. (EP-10-2010VI) | [5 empty] | 3/10-16/2015 |  |  | 06/18-19/2014
Alcorn/Cosco Capital Inc. (EP-07-2010VI) | [5 empty] | 3/10-16/2015 |  |  | 06/18-19/2014
Tambuli Mining Co., Inc. (EP000003VI) |  |  |  | 02/8-9/2016 |  | 3/3-8/2015 |  |  | 02/19-21/2014; 08/5-7/2014
Carles & Cauayan Mining Corp.(EXP000004VI) | [5 empty] | 4/27-5/1/2015 |  |  | 2014-07-12
PGPI/BMC (EP-08-2010VI) | [5 empty] | 4/27-5/1/2015 |  |  | 2014-07-11
San Dominico Min. & Ind'l. Corp. (EP06-2010-VI) | [5 empty] | EXPIRED |  |  | 11/3-4/2014
ISAG
153 Landowners Cooperative |  |  |  | 01/21-31/2016 | none | 3/2-8/2015 |  |  | 2014-03-04
Ban Hua U. Flores |  |  |  | 01/21-31/2016 | none | 3/2-8/2015 |  |  | 2014-03-03
Lilen S. Uy |  |  |  | 01/21-31/2016 | none | 3/2-8/2015 |  |  | 2014-03-04
Mountain Aggregates Inc. | [5 empty] | 1/12-17/2015 |  |  | 2014-02-28
John Alexander I. Gayoso |  |  |  | 02/3-4/2016 |  | 2/9-15/2015 |  |  | 2/10-16/2014
Stephanie O. Chiu |  |  |  | 02/4-5/2016 |  | 2/9-15/2015 |  |  | 2/19-21/2014
Jacareed Enterprises |  |  |  | 01/21-31/2016 | none | 1/12-17/2015 |  |  | 2014-02-25
Anecito Mondia |  |  |  | 01/21-31/2016 | none | 10/19-20 & 26-31/2015 |  |  | New
MPP
Mabini Limers & Farmers Multi-Purpose Coop. | [5 empty] | 5/5-8/2015 |  |  | 2014-04-22
ASPAC Dredging & Restoration |  |  |  | 02/12-13/2016 |  | 2/9-15/2015 |  |  | 2/19-21/2014
Tanden Realty Dev't. Ventures Corp. | [5 empty] | EXPIRED |  |  | 2/19-21/2014
Rocache Aggregate & Dev't. Corp. | [5 empty] | 1/12-17/2015 |  |  | 2014-02-24
Krushrock Corporation |  |  |  | 2016-01-29 |  | 3/2-8/2015; 10/19-20 & 26-31/2015 |  |  | 2014-03-05
Mountain Aggregates Inc. | [5 empty] | 1/12-17/2015; 8/17-27/2015 |  |  | 2014-02-27
GC&C Aggregates, Inc. |  |  |  | 01/21-31/2016 | none | 1/12-17/2015; 8/19-27/2015 |  |  | 2014-02-25
ALH Lime Factory | [5 empty] | 5/5-8/2015; 10/19-20 &26-31/2015 |  |  | 2014-04-28
Malogo Aggregates Ventures, Inc. |  |  |  | 01/21-31/2016 | none | 2/9-15/2015; 8/19-27/2015 |  |  | 2/19-21/2014
Kimwa Const'n. & Dev't. Corp. | [5 empty] | 5/19-23/2015 |  |  | 4/7-13/2014
F. Gurrea Const'n. Inc. | [5 empty] | 5/19-23/2015 |  |  | 4/29-29/2014
ARSD Construction Corporation | [5 empty] | 5/19-23/2015 |  |  | 4/17-13/2014
Skaff Eximport and Services, Inc. | [5 empty] | 5/26-30/2015 |  |  | 2014-05-04
Seven C Integrated Corporation | [5 empty] | 5/5-8/2015 |  |  | 2014-04-25
AWI Concrete Products & Const. Supply | [5 empty] | 5/26-30/2015 |  |  | 4/30-5/1/2014
LGP Builders & Development Corp. | [5 empty] | 5/19-23/2015 |  |  | 4/7-13/2014 | 1 (operating mechanical and electrical installations without Mechanical and Electrical Permit; issued Order of Suspension on Jan. 16, 2014; Order of Suspension lifted on July 2014)
Bernadette Mondejar | [5 empty] | 5/26-30/2015 |  |  | 4/7-13/2014
Maria Aisa B. Ratcliff |  |  |  | 02/6-7/2016 |  | 2/9-15/2015 |  |  | 2/19-21/2014
Panay Mineral Product Resources Corp. | [5 empty] | 10/19-20 & 26-31/2015 |  |  | 2014-04-24
John Bordman Ltd. of Iloilo, Inc. | [5 empty] | 10/19-20 & 26-31/2015 |  |  | 2014-04-23
No. of sites/facilities inspected: | [6 empty] | 13
No. of sites/facilities with 2 inspections for the last 3 years : | [6 empty] | 12
No. of sites/facilities inspected with 1 or more violations over the last 3 years : | [6 empty] | 7
% of sites/facilites with 1 or more violations over the last 3 years: | [6 empty] | 53.85%
% of sites/facilites with more than 2 inspections over the last 3 years: | [6 empty] | 92.31%
Enforcement
PI 1: | Number of Violations or Complaints Acted upon with Reports Issued
PI 2: | Percentage of Submitted Reports that Resulted in the Issuance of Notice of Violations and Penalties Imposed
PI 3: | Percentage of Complaints or Detected Violations that are Acted upon Earlier than the Prescribed Period
Complaint |  | Complainant |  | Date of Filing of Complaint |  | Date Acted Upon on the Complaint |  | Date of Report of Action on Complaint |  | Date of Issuance of Notice of Violation
No. of Violations or Complaints Acted upon with Reports Issued: | [8 empty] | none
No. of Violations or Complaints Acted upon within prescribed period: | [8 empty] | none
No. of notice of violations issued and penalties imposed: | [8 empty] | none
% with notice of violations issued and penalties imposed: | [8 empty] | none
% of Violations or Complaints Acted upon within prescribed period: | [8 empty] | none
Prepared By: |  |  |  |  | Approved by: |  |  |  |  | Date:
CECILIA L. OCHAVO-SAYCON |  |  |  |  | LEO VAN V. JUGUAN, CESO V |  |  |  |  | Feb. 29, 2016
Planning Officer |  |  |  |  | Regional Director

## PIR December
PERFORMANCE INFORMATION REPORT
|  |  |  | Month: | December |  | 2016
MFO I : MINERAL RESOURCES DEVELOPMENT SERVICE
PI 1: | Number of New Mineral Reservation Area Assessed/Endorsed for Declaration (location)
PI 2: | Percentage of Area Surveyed that is Identified as a Mineral Reservation
Location |  |  | Area (Hectares) |  |  | Date of Survey (Geological/ Geographical) |  |  | Area Surveyed (Hectares) |  | %
PI 4: | Percentage of Increase in Peso Value for Royalty Payments Collected
Projected Amount of Royalty to be Collected for 2015 (PhP) |  |  |  | Actual Amount of Royalty Collected for 2015 (PhP) |  |  |  | Percentage Increase (%)
PI 5 : | Percentage of Philippine Territory Surveyed (Geological Exploration) at least once in the Last 3 Years
Location of Area Surveyed |  |  |  | Area Surveyed (Hectares) |  |  |  | Date of Survey |  |  | %
MFO 2 : MINING REGULATION SERVICES
Permit Issuance
PI 1: | Number of Mining Permits/Contracts Issued and Agreements Endorsed for Approval
PI 2: | Percentage of Agreements Entered into within 4 Months from Tendering
Type of Permit/ Contract |  |  | Applicant |  |  | Date Filed |  | Date Issued/ Indorsed |  | Endorsed/Issued w/in 4 Months (Yes/No)
Certification |  |  | Tambuli Mining Co. |  |  | Dec. 7, 2016 |  | Dec. 8, 2016 |  | Yes
Certification |  |  | Tambuli Mining Co. |  |  | Dec. 8, 2016 |  | Dec. 8, 2016 |  | Yes
Accreditation |  |  | J.H. Haulers, Inc. (CA-16-040-VI) |  |  | Dec. 14, 2016 |  | Dec. 15, 2016 |  | Yes
Accreditation |  |  | Diamond Construction Supply and Services (CA-16-041-VI) |  |  | Dec. 14, 2016 |  | Dec. 15, 2016 |  | Yes
Accreditation |  |  | La Pearl's Limestone Products, Construction Services and Supply (CA-16-042-VI) |  |  | Dec. 15, 2016 |  | Dec. 15, 2016 |  | Yes
Accreditation |  |  | SLC Construction Supply (CA-16-024-NIR) |  |  | Dec. 13, 2016 |  | Dec. 15, 2016 |  | Yes
No. of Mining Permits/Contracts issued and Agreements Endorsed for Approval: | [5 empty] | 6 | Permits/Contracts/Agreements issued within 4 months: |  |  |  | 6
[7 empty] | % of Permits/Contracts/ Agreements issued w/in 4 mos. : |  |  |  | 100%
Monitoring
PI 1: | Number of Sites and Facilities Monitored and/or Inspected with Reports Issued
PI 2: | Percentage of Agreements with 1 or More Violations over the Last 3 Years
PI 3: | Percentage of sites that have been inspected more than twice in the last 2 years
Sites/Facilities (Permits/Contracts) Inspected/Monitored |  |  |  | 2016 |  | 2015 |  |  |  | 2014
|  |  |  | Date of Inspection | Number of Violations | Date of Inspection | Number of Violations |  | Date of Inspection | Number of Violations
Work Program
STL Panay Resources Co., Ltd. (CA No. 16-025-VI) |  |  |  | 08/10/2016 * issued on April 22, 2016 |  | --- |  |  | ---
Bulawan Mining Corp. (MLC-MRD No.510) |  |  |  | 09/02/2016 |  | EXPIRED |  |  | 1/29/2014
MPSA
IC Bertumen Co., Inc. (MPSA 231-007VI) |  |  |  | 05/16-29/2016 |  | 2015-03-10 |  |  | 2014-06-19 | Conducting exploration with expired exploration period. Show cause letter was issued on July 30, 2014.
Minimax Min. Expl'n. Corp. (MPSA 135-99VI) |  |  |  | 05/16-29/2016 |  | 2015-03-11 |  |  | 2014-06-17
Silicon Dev't. Corp. (MPSA 204-2004VI) |  |  |  | 02/3-13/2016 |  | 3/3-4/2015 |  |  | 11/3-4/2014
Maricalum Mining Corp. (MPSA 120-98-VI) |  |  |  | Aug. 30- Sept. 4, 2016 |  | 5/1-2/2015 |  |  | 2014-01-27
Philex Gold Phil., Inc. (MPSA 096-97-VI) |  |  |  | Aug. 30- Sept. 4, 2016 |  | 5/1-2/2015 |  |  | 2014-01-29
Selenga Mining Corp. (MPSA 217-2005VI) |  |  |  | Aug. 30- Sept. 4, 2016 |  | 5/1-2/2015 |  |  | 2014-01-30
Quarry Ventures, Phil. Inc. (MPSA 129-98VI) |  |  |  | 05/27/2016 |  | 2015-06-11 |  |  | 2014-09-18
Teresa Marble Corporation (MPSA 097-97VI) |  |  |  | 05/23-28/2016 |  | 6/9-10/2015 |  |  | 2014-09-17
Teresa Marble Corporation (MPSA 107-98VI) |  |  |  | 05/23-28/2016 |  | 2015-06-12 |  |  | 2014-09-16
Tudor Min. Expl'n. Corp. (MPSA 270-2001VI) |  |  |  | 05/16-29/2016 |  | 7/15-22/2015 |  |  | 2014-08-27
Far East Cement Corp. (MPSA 326-2010VI) |  |  |  | 05/16-29/2016 |  | 7/15-22/2015 |  |  | 2014-09-28
Vulcan Ind'l. & Mining Corp. (MPSA 092-97VI) |  |  |  | 10/26-28/2016 |  | 9/23-27/2015 |  |  | 2014-11-06
Vulcan Ind'l. & Mining Corp. (MPSA 113-98VI) |  |  |  | 10/26-28/2016 |  | 9/23-27/2015 |  |  | 2014-11-06
San Dominico Min. & Ind'l. Corp. (319-2010-VI) |  |  |  | Aug. 30- Sept. 4, 2016 |  | 10/19-21/2015 |  |  | 2014-10-04
Dorilag Corp. (MPSA-014-93-VI) |  |  |  | 04/1-2/2016 |  | There has been no operation/activity in the area.
EP
Vale Expl'n. Phils., Inc. (EP-10-2010VI) | [5 empty] | 3/13-14/2015 |  |  | 2014-06-16
Alcorn/Cosco Capital Inc. (EP-07-2010VI) |  |  |  | 11/03/2016 |  | 2015-03-12 |  |  | 2014-06-19
Tambuli Mining Co., Inc. (EP000003VI) |  |  |  | 02/3-13/2016 |  | 3/5-6/2015 |  |  | 2014-10-02
Carles & Cauayan Mining Corp.(EXP000004VI) |  |  |  | Aug. 28, 2016-Sept. 4, 2016 |  | 9/22-27/2015 |  |  | 2014-07-07
PGPI/BMC (EP-08-2010VI) | [5 empty] | 9/22-27/2015 |  |  | 2014-07-09
San Dominico Min. & Ind'l. Corp. (06-2010-VI) |  |  |  | 09/03/2016 |  | 10/19-21/2015 |  |  | 2014-10-03
Philex Gold Phils., Inc. & Bulawan Mining Corp. (EP-08-2010-VI) |  |  |  | Aug. 28, 2016-Sept. 4, 2016 |  | 9/23-24/2015 |  |  | 7/7-11/2014
ISAG
153 Landowners Cooperative |  |  |  | 01/21-30/2016 |  | 2/24-25/2015 |  |  | 2014-02-13
Ban Hua U. Flores |  |  |  | 01/21-30/2016 |  | 2/25-26/2015 |  |  | 2014-02-15
Lilen S. Uy |  |  |  | 01/21-30/2016 |  | 2/27-28/2015 |  |  | 2014-02-14
Mountain Aggregates Inc. |  |  |  | 03/14/2016 |  | 5/28-29/2015 |  |  | 2014-02-07
John Alexander I. Gayoso |  |  |  | 02/3-13/2016 |  | 2015-06-12 |  |  | 2014-07-02
Stephanie O. Chiu |  |  |  | 02/3-13/2016 |  | 9/9-10/2015 |  |  | 2014-11-07
Jacareed Enterprises |  |  |  | 01/21-30/2016 |  | 9/9-10/2015 |  |  | 2014-02-04
Anecito Mondia |  |  |  | 01/21-30/2016 |  | 9/9-10/2015 |  |  | New
MPP
Mabini Limers & Farmers Multi-Purpose Coop. | [5 empty] | 2015-01-22 |  |  | 2014-10-15
ASPAC Dredging & Restoration |  |  |  | 02/3-13/2016 |  | 1/28-29/2015 |  |  | 2014-11-05
Tanden Realty Dev't. Ventures Corp. |  |  |  | 10/12-14/2016 |  | 1/30-31/2015 |  |  | 2014-11-06
Rocache Aggregate & Dev't. Corp. (MPP-010-013-VI) |  |  |  | 03/15/2016 |  | 2015-01-15 |  |  | 2014-02-05
Krushrock Corporation |  |  |  | 01/21-30/2016 |  | 2/23-24/2015 |  |  | 2014-02-12
Mountain Aggregates Inc. (MPP-012-21-VI) |  |  |  | 03/14/2016 |  | 5/27-28/2015 |  |  | 2014-02-08
GC&C Aggregates, Inc. |  |  |  | 01/21-30/2016 |  | 2015-05-30 |  |  | 2014-02-06
ALH Lime Factory | [5 empty] | 7/2-3/2015 |  |  | 2014-10-16
Malogo Aggregates Ventures, Inc. |  |  |  | 01/21-30/2016 |  | 9/9-10/2015 |  |  | 2014-07-01
Kimwa Construction & Development Corporation |  |  |  | 03/9-15/2016 |  | 9/16-17/2015 |  |  | 2014-10-07
F. Gurrea Const'n. Inc. |  |  |  | 03/9-15/2016 |  | 9/16-17/2015 |  |  | 2014-04-04
ARSD Construction Corporation |  |  |  | 03/9-15/2016 |  | 9/23-24/2015 |  |  | 2014-04-30
Skaff Eximport and Services, Inc. |  |  |  | 03/9-15/2016 |  | 9/23-24/2015 |  |  | 2014-04-28
Seven C Integrated Corporation |  |  |  | 03/9-15/2016 |  | 11/4-7/2015 |  |  | 2014-10-17
AWI Concrete Products & Const. Supply |  |  |  | 03/9-15/2016 |  | 11/4-7/2015 |  |  | 2014-05-05
LGP Builders & Development Corp. |  |  |  | 03/9-15/2016 |  | 11/4-7/2015 |  |  | 2014-10-09
Bernadette Mondejar |  |  |  | 03/9-15/2016 |  | 11/4-7/2015 |  |  | 2014-10-10
Maria Aisa B. Ratcliff |  |  |  | 02/3-13/2016 |  | 2015-06-01 |  |  | ---
MMC Marchris Lime Plant |  |  |  | 10/12-14/2016 |  | EXPIRED |  |  | 5/7-9/2014
Integrated Safety, Health, Environment, and Social (ISHES) Monitoring
MPSA
IC Bertumen Co., Inc. (MPSA 231-007-VI) |  |  |  | 05/16-29/2016 |  | 3/10-16/2015 |  |  | 06/21-22/2014
Minimax Min. Expl'n. Corp. (MPSA 135-99-VI) |  |  |  | 05/16-29/2016 |  | 3/10-16/2015 |  |  | 06/19-20/2014
Silicon Dev't. Corp. (MPSA 204-2004-VI) |  |  |  | 02/10-11/2016 |  | 3/2-8/2015 |  |  | 02/19-21/2014
Maricalum Mining Corp. (MPSA 120-98-VI) |  |  |  | 04/13-22/2016; 09/1-10/2016 |  | 4/27-5/1/2015; 9/23-10/3/2015 |  |  | 7/7-8/2014
Philex Gold Phil., Inc. (MPSA 096-97-VI) |  |  |  | 04/13-22/2016; 09/1-10/2016 |  | 4/27-5/1/2015; 9/23-10/3/2015 |  |  | 7/9-10/2014
Selenga Mining Corp. (MPSA 217-2005-VI) |  |  |  | 04/13-22/2016; 09/1-10/2016 |  | 4/27-5/1/2015; 9/23-10/3/2015 |  |  | 1/31-2/2/2014
Quarry Ventures, Phil. Inc. (MPSA 129-98-VI) |  |  |  | 06/1-5/2016 |  | 6/24-7/2/2015 |  |  | 9/19-20/2014
Teresa Marble Corporation (MPSA 097-97-VI) |  |  |  | 05/23-30/2016 |  | 6/24-7/2/2015 |  |  | 2014-09-18
Teresa Marble Corporation (MPSA 107-98-VI) |  |  |  | 05/23-30/2016 |  | 6/24-7/2/2015 |  |  | 9/16-17/2014
Tudor Min. Expl'n. Corp. (MPSA 170-2001-VI) |  |  |  | 05/16-29/2016 |  | 7/15-22/2015 |  |  | 8/20-28/2014
Far East Cement Corp. (MPSA 326-2010-VI) |  |  |  | 05/16-29/2016 |  | 7/15-22/2015 |  |  | 8/26-27/2014
Vulcan Ind'l. & Mining Corp. (MPSA 092-97-VI) |  |  |  | 04/13-22/2016 |  | 9/23-10/3/2015 |  |  | 11/6-7/2014
Vulcan Ind'l. & Mining Corp. (MPSA 113-98-VI) |  |  |  | 04/13-22/2016 |  | 9/23-10/3/2015 |  |  | 2014-11-10
San Dominico Min. & Ind'l. Corp. (319-2010-VI) |  |  |  | 09/1-10/2016 |  | 10/19-20 & 26-31/2015 |  |  | 11/3-4/2014
Dorilag Corp. (MPSA-014-93-VI) |  |  |  | 10/24-26/2016
EP
Vale Expl'n. Phils., Inc. (EP-10-2010-VI) | [5 empty] | 3/10-16/2015 |  |  | 06/18-19/2014
Alcorn/Cosco Capital Inc. (EP-07-2010-VI) | [5 empty] | 3/10-16/2015 |  |  | 06/18-19/2014
Tambuli Mining Co., Inc. (EP-000003-VI) |  |  |  | 02/8-9/2016; 08/30-31/2016 |  | 3/3-8/2015 |  |  | 02/19-21/2014; 08/5-7/2014
Carles & Cauayan Mining Corp.(EXP-000004-VI) |  |  |  | 11/2-3/2016 |  | 4/27-5/1/2015 |  |  | 2014-07-12
PGPI/BMC (EP-08-2010VI) |  |  |  | 11/2-3/2016 |  | 4/27-5/1/2015 |  |  | 2014-07-11
San Dominico Min. & Ind'l. Corp. (EP-06-2010-VI) | [5 empty] | EXPIRED |  |  | 11/3-4/2014
ISAG
153 Landowners Cooperative |  |  |  | 01/21-31/2016; 08/15-26/2016 |  | 3/2-8/2015 |  |  | 2014-03-04
Ban Hua U. Flores |  |  |  | 01/21-31/2016; 08/15-26/2016 |  | 3/2-8/2015 |  |  | 2014-03-03
Lilen S. Uy |  |  |  | 01/21-31/2016; 08/15-26/2016 |  | 3/2-8/2015 |  |  | 2014-03-04
Mountain Aggregates Inc. |  |  |  | 11/4-5/2016 |  | 1/12-17/2015 |  |  | 2014-02-28
John Alexander I. Gayoso |  |  |  | 02/3-4/2016; 10/27-31/2016 |  | 2/9-15/2015 |  |  | 2/10-16/2014
Stephanie O. Chiu |  |  |  | 02/4-5/2016; 10/27-31/2016 |  | 2/9-15/2015 |  |  | 2/19-21/2014
Jacareed Enterprises |  |  |  | 01/21-31/2016; 09/1-10/2016 |  | 1/12-17/2015 |  |  | 2014-02-25
Anecito Mondia |  |  |  | 01/21-31/2016; 08/15-26/2016 |  | 10/19-20 & 26-31/2015 |  |  | New
MPP
Mabini Limers & Farmers Multi-Purpose Coop. |  |  |  | 11/08/2016 |  | 5/5-8/2015 |  |  | 2014-04-22
ASPAC Dredging & Restoration |  |  |  | 02/12-13/2016 |  | 2/9-15/2015 |  |  | 2/19-21/2014
Tanden Realty Dev't. Ventures Corp. | [5 empty] | EXPIRED |  |  | 2/19-21/2014
Rocache Aggregate & Dev't. Corp. |  |  |  | 08/25-26/2016 |  | 1/12-17/2015 |  |  | 2014-02-24
Krushrock Corporation |  |  |  | 01/29/2016; 08/15-26/2016 |  | 3/2-8/2015; 10/19-20 & 26-31/2015 |  |  | 2014-03-05
Mountain Aggregates Inc. |  |  |  | 11/4-5/2016 |  | 1/12-17/2015; 8/17-27/2015 |  |  | 2014-02-27
GC&C Aggregates, Inc. |  |  |  | 01/21-31/2016; 09/1-10/2016 |  | 1/12-17/2015; 8/19-27/2015 |  |  | 2014-02-25
ALH Lime Factory |  |  |  | 11/08/2016 |  | 5/5-8/2015; 10/19-20 &26-31/2015 |  |  | 2014-04-28
Malogo Aggregates Ventures, Inc. |  |  |  | 01/21-31/2016 |  | 2/9-15/2015; 8/19-27/2015 |  |  | 2/19-21/2014
Kimwa Construction and Development Corporation |  |  |  | Feb. 29 - March 10, 2016 |  | 5/19-23/2015 |  |  | 4/7-13/2014
F. Gurrea Construction Inc. |  |  |  | Feb. 29 - March 10, 2016; Oct. 4-15, 2016 |  | 5/19-23/2015 |  |  | 4/29-29/2014
ARSD Construction Corporation |  |  |  | Feb. 29 - March 10, 2016; Oct. 4-15, 2016 |  | 5/19-23/2015 |  |  | 4/17-13/2014
Skaff Eximport and Services, Inc. |  |  |  | Feb. 29 - March 10, 2016; Oct. 4-15, 2016 |  | 5/26-30/2015 |  |  | 2014-05-04
Seven C Integrated Corporation |  |  |  | 06/1-5/2016; 10/24-26/ 2016 |  | 5/5-8/2015 |  |  | 2014-04-25
AWI Concrete Products & Construction Supply |  |  |  | Feb. 29 - March 10, 2016; Oct. 4-15, 2016 |  | 5/26-30/2015 |  |  | 4/30-5/1/2014
LGP Builders & Development Corp. |  |  |  | Feb. 29 - March 10, 2016 |  | 5/19-23/2015 |  |  | 4/7-13/2014 | Operating mechanical and electrical installations without Mechanical and Electrical Permit; issued Order of Suspension on Jan. 16, 2014; Order of Suspension lifted on July 2014
Bernadette Mondejar |  |  |  | Feb. 29 - March 10, 2016; Oct. 4-15, 2016 |  | 5/26-30/2015 |  |  | 4/7-13/2014
Maria Aisa B. Ratcliff |  |  |  | 02/6-7/2016 |  | 2/9-15/2015 |  |  | 2/19-21/2014
Panay Mineral Product Resources Corp. |  |  |  | 11/07/2016 |  | 10/19-20 & 26-31/2015 |  |  | 2014-04-24
John Bordman Ltd. of Iloilo, Inc. |  |  |  | 11/07/2016 |  | 10/19-20 & 26-31/2015 |  |  | 2014-04-23
No. of sites/facilities inspected: | [6 empty] | 0
No. of sites/facilities with 2 inspections for the last 3 years : | [6 empty] | 0
No. of sites/facilities inspected with 1 or more violations over the last 3 years : | [6 empty] | 0
% of sites/facilites with 1 or more violations over the last 3 years: | [6 empty] | #DIV/0!
% of sites/facilites with more than 2 inspections over the last 3 years: | [6 empty] | #DIV/0!
Enforcement
PI 1: | Number of Violations or Complaints Acted upon with Reports Issued
PI 2: | Percentage of Submitted Reports that Resulted in the Issuance of Notice of Violations and Penalties Imposed
PI 3: | Percentage of Complaints or Detected Violations that are Acted upon Earlier than the Prescribed Period
Complaint |  | Complainant |  | Date of Filing of Complaint |  | Date Acted Upon on the Complaint |  | Date of Report of Action on Complaint |  | Date of Issuance of Notice of Violation
Assisted the Military Intelligence Group in the investigation of the alleged illegal mining operations located in Brgy. Barangkalan, Calagna-an Island, Carles, Iloilo |  | Requested by Ezrael M Oloan |  | Nov. 25, 2016 |  | Dec. 13, 2016 -- as scheduled by the MIG |  | Dec. 22, 2016 |  | No activities in the complaint area.
Alleged illegal mining operations in Tapaz, Capiz |  | Leojun Ganit -- as forwarded by the MGB-CO |  | Received on Dec. 7, 2016 |  | Dec. 13, 2016 |  | Dec. 20, 2016 |  | The exact location couldn't be located considering that there was no specific address indicated in the complaint and the LGU-Tapaz had no idea regarding the complaint.
Alleged quarry operations in Sebaste, Antique causing environmental hazards |  | From an anonymous complainant, endorsed by MGB-CO as per memorandum dated Nov. 11, 2016 |  | Received on Dec. 05, 2016 |  | Dec. 13-15, 2016 |  | Dec. 20, 2016 |  | Quarrying outside permit area; referred to ENRO-Antique and EMB
Alleged illegal quarrying/mining at Libertad, Antique |  | Anastacio G. Dugang |  | Dec. 08, 2016 |  | Dec. 15, 2016 |  | Dec. 27, 2016 |  | No operation in the area since the inspection done by ENRO-Antique last Feb. 18, 2016
No. of Violations or Complaints Acted upon with Reports Issued: | [8 empty] | 4
No. of Violations or Complaints Acted upon within prescribed period: | [8 empty] | 4
No. of notice of violations issued and penalties imposed: | [8 empty] | ---
% with notice of violations issued and penalties imposed: | [8 empty] | ---
% of Violations or Complaints Acted upon within prescribed period: | [8 empty] | 100%
Prepared By: |  |  |  |  | Approved by: |  |  |  |  | Date:
CECILIA L. OCHAVO-SAYCON |  |  |  |  | LEO VAN V. JUGUAN, CESO V |  |  |  |  | December 28, 2016
Planning Officer |  |  |  |  | Regional Director